## Slide 1: Human Insights Value Engine (HIVE) Steering Committee
Kick-off meeting
December 2025

## Slide 2: Objectives and Agenda
Agenda
Review meeting objectives
Steering Committee Terms of Reference Review
Project status
Due diligence and key decisions
Delivery structure and technical partner
Estimated costs
Proposed timeline
Global People Data Governance Board
Risks and issues
Summary recap and next steps
Meeting Objectives
Kick-off meeting for HIVE Steering Committee
Confirm Steering Committee Terms of Reference
Review project status
Review due diligence process and gain confirmation on decisions we are moving forward with into implementation
Review proposed HIVE MVP Delivery Structure including technical partner, Nuvento
Review currently estimated project costs
Review proposed project timeline for MVP
Global People Data Governance Board
Review risks and issues
Notes: Kristen

## Slide 3: Steering Committee Terms of Reference
Purpose: The Steering Committee provides strategic direction, oversight and decision-making support for the project and ensures the project is in alignment with organization goals, PACE transformation program goals. The Steering Committee is the decision-making authority for the project and ensures effective resource management.
Frequency: Monthly
Responsibilities:
The Steering Committee is responsible for creating the environment for business change.
The Steering Committee will review project status and key decisions.
The Steering Committee is responsible for resolving strategic issues/conflicts and escalating issues to other senior stakeholder groups as required.
Steering Committee members will provide input, support and challenge as required, ultimately providing assurance of the delivery to time, cost and quality.
The Steering Group will share their input and support the Sponsor who has the decision-making authority.
The Steering Committee will oversee the allocation of resources including budgeting and managing financial risk and will ensure resources are used effectively to meet project goals. They will address bottlenecks and resource issues should they arise
Meeting Inputs (prepared by PM)
Status update – outlining progress, key decisions required, escalations & key risks
Actions from previous meeting
To be circulated in advance of each meeting
Meeting Outputs (documented by the PM)
Record of actions and decisions
Agreed escalations (if any)
Outputs will be provided promptly after each meeting
Attendees
Role | Name | Steering Committee Role
People & Culture COO | Sarah McCann | Executive Project Sponsor
SVP Arch. & App. Delivery | Karthik Ramadoss | Executive Project Sponsor
International CIO | Glenn Feldman | International IT Leadership
People Analytics & Technology Director | Michael Scaduto | Product Owner People & Culture)
Data Services Manager | Rajesh Paul | Product Leadership Data Architecture
Enterprise Architect | Shanna Sommers | Product Leadership Data Architecture
Global People Systems Integrations & Experience Lead | Jamie Shaw | PACE Transformation Leadership – Business Arch
Global People Transformation Lead | Darren Issacs | PACE Transformation Leadership – PMO
Global Change Management Transformation Lead | Beth Truax | Change Management
Project Manager | Kristen Beatty | IT Project Management
Quorum
For the meeting to proceed at least three of the following stakeholders must be present:
Sarah McCann
Karthik Ramadoss
Michael Scaduto
Rajesh Paul
Shanna Sommers
Darren Issacs
Jamie Shaw

## Slide 4: Status Update: HIVE Data Hub Prepared by: Kristen Beatty Date: December 17, 2025
Current Overall Status
Previous Overall Status
G
Executive Summary | Key Decisions Required by Steering Committee
The project is currently in a green status. Key milestones are being met and there are no major risks or issues. Due diligence for HIVE has been completed with Enterprise Architecture, Info Sec, Data Privacy and Compliance. The team is actively engaged with Nuvento, the selected development partner, and reviewing their proposal. Vendor assessment process has been initiated and the MSA review is in progress. The team is targeting to begin implementation in January. | Confirm key decisions made during due diligence (see slide 5 & appendix) Program level Global People Data Governance Board
Activity Complete (October/November/December) | Planned Activity (for next reporting period)
Due diligence kick off meeting held with Enterprise Architecture, Info Sec, Data Privacy and Compliance on November 3 Weekly due diligence meetings held November 10 through December 1 to review and key decisions Finalize key decisions meeting conducted December 8. Key decisions made for MVP data elements, Hosting, Environments, Latency, Security and Governance Team selected Nuvento as the development partner Conducted current state assessment Team testing Fabric functionality in sandbox High-level initial delivery plan developed Team received and reviewed initial proposal. Meeting held on December 11 to review Nuvento’s proposal against refined scope and key decisions. Nuvento will provide updated proposal Vendor assessment process initiated for Nuvento Info sec questionnaires provided to Nuvento. Target completion December 16 MSA review is in progress. Nuvento is reviewing Lockton’s MSA and will provide feedback on December 16 SteerCo kick-off meeting scheduled | Conduct SteerCo kick-off meeting – December 17 Review and confirm key decisions with SteerCo – December 17 Complete vendor assessment/due diligence for Nuvento Finalize MSA & SOW Develop onboarding plan for Nuvento and initiate onboarding Finalize MVP delivery plan and resources needed Review MVP resource requirements with Resource Managers and put into capacity planner Develop proposed MVP implementation plan Engage Beth to begin conversations on changes required to data gathering process Continue work on infrastructure for dev and test environment Begin planning discussions on backlog, HCM integrations and Phenom integrations

## Slide 5: Due Diligence Process We Followed
Workshop/KDD | Date/Time | Agenda | Outcome | Lockton Attendees
Due Diligence Kick-Off Meeting | Monday, 11/3 Recording: Link | Overview of HIVE Review scope and design Key Decisions Due Diligence Process and Resources | Team is aligned on plan Feedback on KDD’s and resources DECISION 1: Create rules table to allow data field by country to adhere to regulations in MVP | Aaron All, Kristen Beatty, Craig Bexon, Travis Harder, Darren Isaacs, Collette Hope, Claudia Greim, Rosie Mitchell, Rajesh Paul, Michael Scaduto, Jamie Shaw, Sandrya Moore, Shanna Sommers, Lizzy Thomas
HIVE Hosting Plan | Monday, 11/10 Recording: Link | Status on Networking work for Global tenant Review data plans and requirements Discuss Regulatory Rules Hosting options | DECISION 2: Hosting location - US | Damien Blue, Jessica Burche, David Collins, Travis Harder, Collette Hope, Claudia Greim, Rajesh Paul, Michael Scaduto, Jamie Shaw, Sandrya Moore, Karthik Ramadoss, Shanna Sommers, Lizzy Thomas, Beth Whitehand
Environment requirements & latency | Monday, 11/17 Recording: Link | Confirm environments – DEV, TST, PRD HIVE Users and needs Hosting location, users, usage | DECISION 3: Environment needs for MVP DEV. TST, PRD DECISION 4: Address Latency adhoc if needed | Aaron All, Kristen Beatty, Damien Blue, Jessica Burche, David Collins, Travis Harder, Raoul Hira, Claudia Greim, Rosie Mitchell, Rajesh Paul, Karthik Ramadoss, Michael Scaduto, Jamie Shaw, Shanna Sommers, Lizzy Thomas
Security – Process and technical requirements and ongoing governance | Monday, 12/1 Recording: Link | Review access expectations Discuss options to solve process or system Ongoing governance – who and how | DECISION 5: High level Security requirements cover the needs and will refine during implementation DECISION 6: Ongoing governance board for People data will be created | Kristen Beatty, Damien Blue, David Collins, Rosie Mitchell, Sandrya Moore, Rajesh Paul, Karthik Ramadoss, Michael Scaduto, Jamie Shaw, Shanna Sommers, Lizzy Thomas, Beth Whitehand
*Links to meeting decks
*Links to meeting recordings
*Links to detailed Decision Documents

## Slide 6
Proposed HIVE MVP Delivery Structure
Executive Committee
Karthik Ramadoss
Product Leadership
Shanna Sommers
Jamie Shaw
Michael Scaduto
Project Manager
Kristen Beatty
Process Workstream
Beth Whitehand
Sarah Enfield
Michael Scaduto
Fiona Morris
Data & Technology Workstream
Fiona Morris
Michael Scaduto
Rajesh Paul
Business Architecture
Erik Vizcaino
Shane Strong
Vicky McKendrik
Megan Matile
PACE Transformation Leadership
Darren Issacs
Shanna Sommers
Nuvento
Engagement Director
Ongoing Governance
Global InfoSec
UK Data Privacy
Enterprise Architecture
Global People Systems and Data
Others? TBD
Claudia Greim
Michael Scaduto
IT Data Services
Jessica Burche
Rajesh Paul
Global Compliance
Raoul Hira
Jamie Shaw
Rajesh Paul
Cloud Engineering
Solutions Architect
Business Analyst
Project Manager
Data Engineers/QA
DevOps/Security Engineers
Web App Developer
Training/Hypercare
US
Offshore
Business
IT
Others? TBD
Networking

## Slide 7: Current Estimated Project Costs
Updated proposal received from Nuvento. Team review scheduled on December 18
Current estimates costs are shown below:

## Slide 8: High level proposed implementation timeline (MVP)*
November - December
February
January
March
Due diligence sessions conducted
Team testing Fabric functionality in sandbox
Nuvento proposal review – in progress
Initiated vendor assessment for Nuvento
High-level implementation timeline developed
HIVE steering committee kick-off meeting
Initial onboarding plan developed
Complete vendor assessment for Nuvento
Finalize MSA & SOW with Nuvento
Develop proposed MVP implementation plan
Finalize MVP delivery plan and resources needed including capacity planning
Begin change management conversations
Continue work on infrastructure for dev and test environment
Onboard Nuvento resources
April
May
Development
Data privacy & compliance reviews
Test planning
Execute on change management plan
Conduct training on new template and data field requirements
Project kick-off
Conduct analysis
Review and Fabric set-up
Requirements and design
Data privacy & compliance reviews
Change management planning
We are here
Complete development
Data privacy & compliance reviews
Conduct validation
Performance testing
UAT testing
Conduct Admin Training
Go-Live
* NOTE: This is a proposed timeline. It is pending the formal engagement with Nuvento and needs to be reviewed with the project team
Hypercare
Change management updates
Begin backlog
Begin Phenom integrations

## Slide 9: Global People Data Governance Board
01
Purpose and Objectives
The purpose of this cross functional board is to establish ongoing unified oversight and strategic direction for the management of Lockton’s global People data, The objective will be to ensure compliance with evolving data regulations, maintain data quality and security, and foster cross-functional collaboration.
02
Authority
Approve or reject proposed policies, standards, and technology design for use of People data globally.
Ensure compliance with evolving regulations and organizational needs.
Oversee and direct remediation actions for data quality, security, or compliance issues.
Escalate unresolved data governance matters to the appropriate executive leadership.
03
Membership
People & Culture Systems and HR Operations, as needed
Compliance, Data Privacy and Legal advisors, as needed
Information Security
IT Data Leader
Other subject matter experts or stakeholders as required by agenda
04
Deliverables
Global People data governance policies, standards, and procedures
Regular compliance and data quality reports
Recommendations for regulatory updates and required process changes
Documentation of approved data management practices and decisions for transparency and accountability
Action plans for remediation of data issues or risks
We recommend establishing a Global People Data Governance Board as follows:

## Slide 10: Risks and Issues Prepared by: Kristen Beatty Date: December 17, 2025
Top Risks and Issues |  |  |  | 
Workstream (Owner) | Description | Mitigation Plan | Priority | Status
Kristen Beatty | Vendor Assessment/Due Diligence: Risk Nuvento is a new development partner and will need to complete global vendor assessment/due diligence. There is not a clearly defined process for global vendor assessment/due diligence. This could cause a delay in signing the contract with Nuvento and could impact the start for MVP implementation. | The Lockton PM is managing Nuvento through the vendor assessment/due diligence process. Target completion in January to allow development to begin by the beginning of February. | High | In Progress
Michael Scaduto/ Fiona Morris | Ingestion and Transformation Mapping Rules & Rules Engine: Risk Global People Data & Analytics will need to define the ingestion rules and transformation rules detailed requirements for the build. The rules are potentially complex and will need to be accurately defined to enable the build. A user interface will need to be developed to support business users adding in additional rules versus development required. | Fiona is gathering current mapping requirements and documenting current transformations that are performed manually. Deep dive requirements sessions will be conducted with the Nuvento Business Analyst and the Lockton Business Analyst. A user interface is included in the requirements for Nuvento to build. | High | In progress
Michael Scaduto/ Fiona Morris | Process Change Required (Change Management): Risk Regions will be required to adopt a standardized data template for their data to get processed in HIVE. Even though the regions are provided a standard template today, they do not consistently use it. Regions will be required to put the data in the correct format in the standardized template, or the data will be rejected in HIVE. Change management will be required to roll out required template and data field requirements. | Engage Beth to develop a change management plan including communications and training to support the rollout of the standardized template and required data elements. The template will need to be adopted for testing. | Medium | Not started
Jamie Shaw/ Kristen Beatty | Data privacy & compliance reviews required during implementation: Risk The implementation plan needs to include sufficient time for due diligence/reviews with internal Lockton SMEs like data privacy and compliance at different stages, especially after design, before deployment, etc. These reviews could impact the timeline if there are delays. | Implement a PACE program Global People Data Governance Board to provide structured oversight for People data and AI. Lockton PM will need to partner with Nuvento PM to build time into the project schedule to allow the reviews to occur. If the team experiences delays, the Lockton PM will escalate to leadership to help resolve. | Medium | In progress

## Slide 11: Risks and Issues Prepared by: Kristen Beatty Date: December 17, 2025
Top Risks and Issues |  |  |  | 
Workstream (Owner) | Description | Mitigation Plan | Priority | Status
Jamie Shaw | Global People Data Governance Board: Risk As part of due diligence, the team determined a governance board is needed to provide structured oversight for People data from a Compliance, Data Privacy and InfoSec perspective. This overlaps with the need for a data governance board with the Phenom project. This board does not exist yet. | Implement a PACE program Global People Data Governance Board to provide structured oversight for People data and AI. | Medium | In Progress
Rajesh Paul/ Kristen Beatty | Nuvento resourcing model: Risk Team will use a mixture of onshore and offshore resources with mostly offshore resources currently proposed. The time zones do not align well with our US based resources. | Nuvento will schedule resources that will overlap with Core US Business hours and will provide an onshore Solutions Architect. Lockton team will get clarification if Nuvento will be providing a US based Engagement Director as well. | Low | In Progress

## Slide 12: Recap
Finalize Nuvento MSA & SOW
Complete Nuvento due diligence and onboarding
Update the HIVE implementation plan
Identify required resources and plan team capacity
Initiate change management conversations
Schedule recurring Steering Committee meetings
Kick off the HIVE MVP Implementation project (Target: February 2026)
Begin separate due diligence processes for Phenom and Cornerstone projects which will involve HIVE for integrations (TBD) – starting in January 2026
Next Steps
Summary
HIVE is Lockton’s internally built global People data repository, integrating legacy HCM sources and enabling connections to platforms like Phenom, Cornerstone, and Workday.
HIVE will be hosted in the US, ensuring optimal performance and regulatory compliance for the largest user base. Regulatory compliance outside of US will be ensured through data privacy agreements.
MVP will launch with dedicated DEV, TST, and PRD environments; additional environments will be added post MVP go-live.
Data field acceptance will be managed by a configurable rules engine, supporting country- and region-specific compliance.
Security and governance will be refined during implementation, with oversight from a formal Global People Data Governance Board.
Latency and performance will be monitored and addressed as needed to support rapid delivery and future scalability.
Nuvento is the implementation partner that we are beginning Due Diligence, contracting and onboarding in January for a February kick-off.
.

## Slide 13: Appendix

## Slide 14: Risks and Issues - Closed Prepared by: Kristen Beatty Date: December 17, 2025
Top Risks and Issues |  | 
Workstream (Owner) | Description | Mitigation Plan
Rajesh Paul | New IT components and experience levels: Risk Microsoft Fabric and Purview are new technologies for Lockton. Our team has limited knowledge regarding these two products | Closed - Our resources are currently working in sandbox to learn Microsoft Fabric and Purview We will partner with Nuvento to supplement our resources
Kristen Beatty | IT Resource availability: Risk Potential IT resource capacity constraints. | Closed – Team has engaged Nuvento to supplement existing Lockton IT resources
Rajesh Paul Kristen Beatty | Nuvento’s understanding of the HIVE MVP scope: Risk Nuvento will need to fully understand the HIVE MVP scope to accurately bid, develop a proposed implementation plan and resource the project. | Closed - The team met with Nuvento on December 12 to review the scope and current proposal. Nuvento team provided an updated proposal on December 15. The project team will review the current proposal to ensure it accurately captures the scope. Review scheduled December 18.
Rajesh Paul | Infrastructure set up required: Risk Product Infrastructure and Dev Ops need to set up the infrastructure for Nuvento to be able to begin the development by February | Closed: IT Resource managers are identifying additional resources required to complete the set-up. If the set up is lagging behind schedule, Nuvento can begin with requirements sessions
Michael Scaduto/ Jamie Shaw | Lockton BA: Issue A Lockton BA is needed to support this project. We do not have a Lockton BA available. We need to determine if HRIS can support this or if an IT BA is needed. | Closed – Will be resourced from Business Architecture team

## Slide 15: HIVE Microsoft-based Ecosystem
This diagram provides a step-by-step process of the unified data integrations with legacy HCM systems and downstream systems, mapping the data both for inbound and outbound integrations for unified data.
This diagram provides a step-by-step process of the unified data integrations with legacy HCM systems and downstream systems, mapping the data both for inbound and outbound integrations for unified data.
Receive and Validate
1
4
3
Mapping unified data
Integration Service
2
Generate output in Target format
Downstream Systems
5
PGP Decryption
Source System
Data Hub Ecosystem
Error handling & Notification framework
Azure
Data Entry/Exit
PeopleSoft
Integration Monitoring
Bmboo HR
BIPO
ResourceLink (Zellis)
ADP
Web HR
Excel
6
Receive
Phenom
Load and Import
Receive
Cornerstone
Load and Import
Receive
Flexible placeholder for future global integration business needs that are not specifically identified yet
Load and Import
Data Entry/Exit
Receive
Load and Import
Perceptex
Global People and org data repository that stores and handles transformation, mapping and file formatting.
Global People Analytics will be sourced in Data Hub
File Transfer or API based on downstream system
Integrations triggered based on schedule configured
Legacy HCM systems continue to serve as the primary platform
Users still interact through their legacy system interface
Interfaces and analytics are maintained locally for region data.
Integrations triggered based on schedule configured
MVP
Backlog
Project
Security

## Slide 16: Updated Proposed Product Approach after Due Diligence – Scope by Phase
Phase 1 MVP
January 2025 – May 2026
Backlog
FY27
Project Specific
FY27 – FY29
Create centralized global data repository through ingestion of data files from a standardized existing excel template saved in designated TEAMS/SharePoint folder
Rules engine that allows the data to be accepted or not at the Region, Country or Business Unit level based on data privacy regulations.
Transform raw data from data files (populated from legacy HCM systems or manually) into a unified global data based on rules defined by business administrators. These rules will be used to align with Global Chart of Accounts and Global organization.
Provide a user interface to create, edit or delete Regulatory or Mapping rules for HR Business Administrators
Set up security profiles and audit logs
Define on-going governance process for data security compliance
Enable People Analytics through PowerBI/Tableau
Optimize performance of system usage
Automate processing with Legacy HCMs through applicable integration method (file feed or API). To be prioritized:
  PeopleSoft (US)
  ResourceLink (UK)
  BIPO (Asia)
  WebHR
  BambooHR (Mexico)
  ADP (Pacific)
Enhance centralized data repository by adding in Engagement data. Examples:
  Perceptyx
  Enboarder
Enhance centralized data repository by adding in Compensation data. Examples:
  Payscale
  Market Data
  LTI Data
Phenom integrations
Cornerstone integrations
Workday integrations

## Slide 17: KEY DECISION: Data Fields Regulatory
Description of Design Decision: |  | 
How and when to define which data fields are accepted into HIVE to comply with regulatory rules for each country, region, or business unit. Decide whether to start with configurable rules for data field acceptance managed by People and Culture, or to use hard-coded rules, setting the foundation for regulatory compliance and future flexibility. |  | 
Solution Option #1: Universal Data Field List Defined During Due Diligence and a rules mapping table or hard coding location based rules would be added to the backlog. |  | 
Advantages: Simplifies implementation with a fixed data model. Reduces complexity in ongoing management. Provides clarity and consistency for all stakeholders. | Disadvantages: May result in over-restriction, excluding valuable data for some regions. Difficult to maintain compliance as regulations change. Limits flexibility for future integrations and business needs. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Due diligence phase extended, but implementation quicker | Lower MVP costs and increased long-term costs. | Fewer resources MVP, Increased resource for future updates
Solution Option #2: Configurable Rules Engine (Mapping Table) Defined During Implementation |  | 
Advantages: Enables granular compliance with local regulations. Provides flexibility to adapt to changing laws and business requirements. Supports future integrations and evolving business needs. Allows business administrators to manage rules through a user interface. | Disadvantages: Requires more effort during implementation to define and test rules. Adds complexity to the system and ongoing governance. Needs robust auditing and change management processes. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Development costs | More build and testing | Development resources and ongoing management
RECOMMEND
Detailed Decision Document with rationale

## Slide 18: KEY DECISION: Hosting Location
Description of Design Decision: |  | 
Choosing HIVE’s hosting location is a critical decision that will shape Lockton’s People and Culture technology landscape, influencing future platform integrations and ensuring alignment with global data and compliance needs. |  | 
Solution Option #1: Host in US |  | 
Advantages: Largest user base and data volume no latency threat to majority of users with most extensive use cases. Current state, ready to start build Employment data can bypass regulatory challenges through agreements | Disadvantages: Potential latency threat to global users and data. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Fastest and easiest timeline with no net new Microsoft infrastructure dependency that could risk HIVE MVP timeline | Eliminates risk to budget for unknown global Msoft tenant MVP | Positive impact – no need for Networking resources
Solution Option #2: Global tenant with subscription to Msoft datacenter in Dublin |  | 
Advantages: GDPR compliance UK/Europe – no latency threat for users located in that region, | Disadvantages: Potential latency in US and globe | 
Impact: Timeline | Impact: Budget | Impact: Resources
Dependent on networking requirements to stand up Global Tenant. Est comp Dec 2025. HIVE build estimated to start in Jan 2026. | Unknown | Networking resources
RECOMMEND
Detailed Decision Document with rationale

## Slide 19: KEY DECISION: Environment needs
Description of Design Decision: |  | 
Establish Development, Test, Production, and decide timing of a protected Staging environment that mirrors Production and will be used for validating mapping tables and rigorous testing before deploying changes to Production. |  | 
Solution Option #1: Build DEV, TST, PRD for MVP only and additional environments if needed with project |  | 
Advantages: Fastest time to market; avoids over-engineering for MVP. Minimizes initial resource and budget requirements. Aligns with historical practice (e.g., PeopleSoft), where new environments are added as projects require. Allows the team to learn and adapt before expanding environment complexity. | Disadvantages: May require urgent creation of new environments if parallel development or advanced testing needs arise. Risk of configuration changes or mapping table updates impacting production if not adequately tested. Potential for bottlenecks if multiple workstreams need isolated environments. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Accelerates MVP delivery | Lower initial spend; future costs if new environments are needed. | Minimal upfront resource allocation
Solution Option #2: Build Core + Staging Environment for MVP |  | 
Advantages: Enables more robust testing and validation, reducing risk of production issues. Supports parallel development and configuration changes without impacting Production. Proactively addresses anticipated future needs as HIVE evolves and integrates with other platforms. | Disadvantages: Higher initial resource and budget requirements. Adds complexity to MVP build and environment management. May be overkill if MVP requirements remain simple or if future needs are less than anticipated. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Slightly longer MVP delivery due to additional setup | Higher upfront investment; may reduce future costs | Requires more technical and support resources initially
Detailed Decision Document with rationale

## Slide 20: KEY DECISION: Security Approach
Description of Design Decision: |  | 
Define how HIVE’s security will be implemented through technology, process, or a combination. This includes validating that proposed requirements are feasible and sufficient, and accounting for any additional tools, budget, or resources needed to meet compliance, data protection, and access control expectations. |  | 
Solution Option #1: Accept the proposed high-level security approach and proceed to refine and finalize the detailed design during the implementation. |  | 
Advantages: Enables the project to move forward without delaying the MVP timeline. Provides flexibility to refine details as technical and business requirements evolve. Reduces upfront effort during due diligence, focusing on strategic alignment rather than exhaustive design. Allows implementation team to incorporate lessons learned and best practices during build. | Disadvantages: Higher risk of scope changes later, which could impact timeline or budget. Limited clarity for stakeholders now, which may cause uncertainty about compliance readiness. Potential for missed requirements if not tracked rigorously during implementation. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Accelerates MVP delivery | Lower initial investment; possible future costs if changes are needed | Minimal upfront allocation; may require additional resources later.
Solution Option #2: Continue to develop and finalize the security approach within the due diligence phase before moving to implementation. |  | 
Advantages: Provides clear, detailed requirements upfront, reducing ambiguity for implementation. Strengthens confidence in compliance and data protection before build begins. Minimizes risk of costly changes later in the project. | Disadvantages: Extends due diligence timeline and requires additional resources now. May delay MVP start if design decisions take longer than expected. Less flexibility to adapt to new insights or evolving business needs during implementation. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Longer due diligence; possible delay to MVP launch. | Higher upfront investment; may reduce future change costs. | Requires more technical and compliance resources upfront.
RECOMMEND
Detailed Decision Document with rationale

## Slide 21: KEY DECISION: Latency
Description of Design Decision: |  | 
Proactively build solutions to minimize latency for all key personas before MVP launch, or to proceed with the selected hosting location and address latency issues reactively as they arise. |  | 
Solution Option #1: Address Latency Issues as They Arise (Reactive Approach) |  | 
Advantages: Enables immediate progress without waiting for exhaustive latency analysis. Avoids unnecessary upfront investment in mitigating issues that may not materialize. Allows real-world data to inform future decisions. | Disadvantages: Latency issues may impact user experience or integrations unexpectedly, requiring urgent fixes. May result in reactive spending or rushed solutions if problems arise post-launch. Risks to business continuity if latency becomes a showstopper for key users or processes. | 
Impact: Timeline | Impact: Budget | Impact: Resources
Fast MVP rollout; potential delays if latency issues require remediation. | Lower initial spend; unpredictable future costs if issues arise. | Minimal upfront allocation; future spikes if urgent fixes are needed.
Solution Option #2: Proactively Plan and Budget for Latency Mitigation (Proactive Approach) |  | 
Advantages: Reduces risk of negative user experience or business disruption. Enables smoother scaling and integration with global platforms (e.g., Workday, Phenom). Supports strategic alignment with future technology roadmap. | Disadvantages: Will not know if there are any issues until MVP is in process Adds time and effort that may not have an ROI before something is delivered to production even if latency becomes a show stopper and requires addressing though a change request | 
Impact: Timeline | Impact: Budget | Impact: Resources
Longer MVP delivery due to additional planning and implementation. | Higher initial investment | Requires technical expertise and cross-team collaboration upfront.
Detailed Decision Document with rationale

## Slide 22: KEY DECISION: Governance Board
Description of Design Decision: |  | 
Determine whether Lockton should establish a formal Global People Data Governance Board to provide structured oversight for People data or continue managing governance through ad hoc engagement across existing groups. |  | 
Solution Option #1: Establish a Global Data Governance Board |  | 
Advantages: Provides unified oversight and strategic direction for globally scoped People data Ensures compliance with evolving regulations through a structured, proactive approach. Facilitates cross-functional collaboration and transparency across People & Culture, IT, Compliance, and Security. | Disadvantages: Requires ongoing time commitment and resources for governance activities. Potential overlap with other governance structures (e.g., Digital initiatives), creating risk of redundancy. May slow decision-making if processes are overly formalized. | 
Impact: Timeline | Impact: Budget | Impact: Resources
N/A | N/A | TBD
Solution Option #2: Do Not Create a Governance Board; Manage via Ad Hoc Engagement |  | 
Advantages: No additional governance structure or resource investment required. Faster, informal decision-making for urgent issues. Flexibility to involve only relevant stakeholders as needed. | Disadvantages: Fragmented approach increases risk of non-compliance and inconsistent decisions. Limited visibility and accountability for global People data management. Reactive rather than proactive, making it harder to keep pace with regulatory changes. Decisions may conflict with enterprise solutions or create downstream impacts without coordination. | 
Impact: Timeline | Impact: Budget | Impact: Resources
N/A | N/A | TBD
RECOMMEND
Detailed Decision Document with rationale