# Hackathon Retrospective - Lessons Learned

GAS 2026 Hackathon - Jan 14, 2026

Retro meeting: Jan 27, 2026

## Executive Overview

I conducted a retrospective with the India team (Chennai & LGCC) and received excellent, detailed feedback. While the hackathon had great energy and strong team engagement, we encountered significant challenges with infrastructure setup, timing, and challenge management that prevented teams from delivering their full potential. The positive news is that the India team has extensive hackathon experience from H&R Block and shared valuable best practices.

Key Takeaway: With months of proper planning and implementation of the recommendations below, future hackathons can become a cornerstone of Lockton's innovation culture. H&R Bloch India has achieved single-digit attrition with employees partly due to their hackathon culture where people see their work come to life.

## What Went Well

- Exceptional team energy and engagement - Participants were highly invested in their projects, creating strong motivation throughout the event

- Effective cross-domain collaboration - Having team members from different domains significantly improved coordination and knowledge sharing

- Quality challenge statements - Challenges helped teams understand real business needs and pain points

- Overall positive experience - Despite infrastructure challenges, participants gained clarity on leadership priorities and business requirements

- Winning team demonstrated resilience - The winning team had to switch challenges at the last minute due to POC withdrawal and still delivered an excellent solution

## Critical Areas for Improvement

### 1. Infrastructure & Environment Setup

What happened:

- Teams had inconsistent access to resources - some had Dataverse access while others didn't; some could use premium connectors, others couldn't; publishing capabilities varied by team

- This created significant frustration and a perception of unfair competition

- Work order was submitted 3 weeks before the event, but setup wasn't completed until the Friday before Tuesday's event - no buffer time for testing

- No infrastructure engineers were available during the event to resolve access issues in real-time

- No predefined rules document explaining what services and resources were available

Impact:

- Teams invested time in solutions they ultimately couldn't implement

- Uneven playing field undermined the competitive spirit

- Participants were unable to deliver their best work due to technical constraints

### 2. Point of Contact & Challenge Management

What happened:

- Single POCs were assigned to 3-4 challenges simultaneously (notably Thomas Nichols), making it difficult to provide adequate support

- Some POCs returned from holiday break and prioritized regular work over hackathon support, leading to challenge withdrawals

- This forced teams to switch challenges mid-preparation, wasting their prep work

- No explanatory videos were provided for challenges

- Sample data arrived in the last week

- Documentation was minimal

Impact:

- Teams spent valuable development time trying to understand requirements instead of building solutions

- General frustration with the preparation process

### 3. Event Timing

What happened:

- Event was scheduled for January 14 - only 3 weeks after Christmas/New Year holidays

- Many people take 2+ weeks off during this period

- When POCs returned, they prioritized catching up on regular work over hackathon preparation

- Teams developed all day and had to present immediately afterward while exhausted

Key Learning: Avoid scheduling within 3 weeks of major holidays

## Recommendations for Future Hackathons

### Infrastructure Setup (Lead Time: 2 Months)

Templated approach:

- Create one test environment and test thoroughly with a sample team

- Replicate the exact same setup for all teams

- This ensures consistency and identifies issues early

- Complete all setup 1 week before the event minimum to allow for comprehensive testing

Rules documentation:

- Document all available resources: premium connectors, Dataverse access, publishing capabilities, data access, etc.

- Verify that every team has identical access and capabilities

- Ensure no team has an advantage or disadvantage based on infrastructure

Support requirements:

- Assign 2-3 dedicated infrastructure engineers to be available during the entire event

- Teams should not lose competition time due to technical issues

- Leverage Aaron's team and their LGCC counterparts who have infrastructure expertise

Pre-event information session:

- Hold a session before the hackathon where infrastructure team explains what's in scope vs. out of scope

- Allow time for questions and boundary clarification

### Challenge Management (100% complete 4-8 weeks before Hackathon)

POC assignment rules:

- One POC per challenge maximum - no exceptions

- Obtain written commitment from POCs 6-8 weeks before the event

- Secure manager approval confirming they can dedicate time to this effort

- Identify a backup POC for each challenge

- If a POC cannot fully commit, remove the challenge - quality over quantity

POC responsibilities:

- Create 10-15 minute video explaining the challenge (why it matters, current process, desired outcome)

- Prepare comprehensive documentation: problem statement, process flows, sample data, success criteria, background materials

- Hold optional office hours 2-3 days before the event (30-minute Q&A sessions)

Sample data:

- Provide data guidelines at the beginning of the preparation period, not in the final week

- Teams need sample data early to understand data structures and plan their solutions

### Event Timing & Format

Optimal timing:

- Do not schedule within 3 weeks of major holidays (Christmas/New Year, Thanksgiving, etc.)

- Best windows: February-April or September-November

- These periods have more stable work schedules and make it easier to secure POC commitments

24-hour hackathon format (Strongly recommended by India team):

Quote from Karan Khot: "Hackathon is like rallying your troops and going to war. We expect people to be battered up because what it builds is camaraderie. Teams come out after 24 hours more excited than when they started."

Benefits of 24-hour format:

- Builds authentic team bonding through shared intense experience

- Teams develop better solutions with continuous work vs. fragmented time

- Captures the true essence of a hackathon - immersive innovation challenge

- Enables global participation with overlapping time zones

- Teams work through problems together, building engineering skills and resilience

Brain breaks during the event:

- Provide activities to help teams refresh: chess, foosball, ping pong, darts, Lego building

- Short breaks keep energy high and encourage cross-team interaction

Alternative if 24-hour format not feasible:

- Split Day 1 (development) and Day 2 (presentations)

- Note: This approach loses some of the immersive team-building experience

### Cultural Best Practices from H&R Block India

Food variety:

- Provide varied menus for breakfast, lunch, dinner, and late-night snacks

- Food variety becomes part of the positive experience and something participants look forward to

Challenge categories:

- Open Category: Teams create their own problems and solutions - encourages pure innovation

- Business Category: Specific company problems that need solutions - provides direct business value

- Consider separate hackathons or at minimum, separate judging categories for each type

Post-hackathon implementation (CRITICAL):

- Actually implement winning solutions - don't let them die after the event

- Give participants the opportunity to work on implementing their solutions

- At H&R Block, some people changed teams to work on their hackathon projects

- This is what sustains hackathon culture and contributes to H&R Block's single-digit attrition rate with 2000+ employees

## Action Items Checklist

3 Months Before Event:

- Identify infrastructure team (both US and LGCC representatives)

- Document all required services and resources for challenges

- Secure POC commitments (one per challenge only)

- Obtain manager approval for POC time commitment

- Identify backup POCs for each challenge

- Finalize event date (avoiding post-holiday periods)

6 Weeks Before Event:

- Create and test template sandbox environment with sample team

- POCs create 10-15 minute video recordings explaining challenges

- POCs prepare comprehensive documentation packages and sample data

1 Month Before Event:

- Replicate template environment for all teams

- Verify identical configuration across all team environments

- Distribute challenge documentation and videos to all participants

- Publish resource availability document (in scope/out of scope)

2 Weeks Before Event:

- Complete all environment setup and configuration

- Conduct comprehensive smoke test with all participants

- Resolve any access or configuration issues discovered in smoke test

- Hold POC office hours for teams to ask clarifying questions

- Confirm infrastructure support team availability for event day

Day of Event:

- Infrastructure team on-site and available throughout event

- POCs available for questions during development time

- Brain break activities set up (chess, foosball, ping pong, etc.)

- Food and refreshments ready (varied menus for all meals)

Post-Event Follow-Up:

- Schedule follow-up meeting with leadership (Shanna, Karthik, Dilip)

- Evaluate winning solutions for implementation feasibility

- Create implementation plan for viable solutions

- Conduct retrospective with all participants

- Document lessons learned for next event

## Next Steps

Potential March 2026 visit to LGCC/Chennai:

- Awaiting budget approval to travel with Lockton group

- Trip would include 1-2 days in LGCC and remainder in Chennai

- Purpose: Direct knowledge transfer from the India team's extensive hackathon experience

H&R Bloch knowledge sharing:

- Karan has offered to arrange meetings with H&R Block hackathon organizers

- Opportunity to learn from their proven model with measurable business impact

- H&R Block India: single-digit attrition, high employee engagement

Leadership alignment:

- Schedule follow-up meeting with Shanna, Karthik, and Dilip

- Discuss implementation path for winning solutions

- Plan next hackathon incorporating all lessons learned

Future hackathon timing:

- Potential dates: February-April 2027 or September-November 2026

- Ensure at least 3 weeks separation from major holidays

## Key Insights & Acknowledgments

- Despite challenges with infrastructure and timing, the hackathon successfully brought teams together and created enthusiasm for innovation

- The 24-hour format is strongly endorsed by the India team based on extensive experience

- Post-event implementation is the critical factor in building sustainable hackathon culture

- H&R Block's success demonstrates the business value: 2000+ employees with single-digit attrition, partly attributed to hackathon culture

## Decision Point: Open vs. Business-Focused Challenges

Team perspective:

- Puru suggested considering separate hackathons for open-ended vs. business-focused challenges

- These have different goals and different deliverables

- Open-ended: Fresh ideas, no predefined constraints

- Business-focused: Solving existing problems with clear deliverables

Options to consider:

- Separate events for each type

- Single event with separate award categories

- Mix both types in one competition

Retrospective conducted with:

Puru Kumar (Chennai), Karan Khot (LGCC), Akash John (LGCC), Rajeev Gopalakrishnan (LGCC)

January 27, 2026